## Quick Start
GMP Audit Readiness Working File
Turn a bounded audit scope into owned evidence requests, gaps, due dates and review decisions.
Workbook version | 2.0.0-review
Variant | Fictional completed example
Review status | Under review
Risk boundary | Decision support; authorized site review remains required
Step 1 | Confirm intended use and accountable owner
Step 2 | Enter facts and evidence references in yellow cells
Step 3 | Resolve formula-driven attention flags
Step 4 | Record reviewer role and approval outside Atlas
Color legend: yellow = user input ¦ blue = formula/check ¦ green = externally approved state ¦ red/amber = unresolved attention
Limitations: This workbook does not replace an approved SOP, site risk assessment, QA disposition, current licensed standard, validation, or regulatory review. Fictional examples contain no client data.

## Working Register
GMP Audit Readiness Working File
Fictional example - adapt only after qualified site review.
Item ID | System / area | Evidence request or control | Risk | Due date | Owner role | Status | Evidence reference | Reviewer role | Notes | Attention
AUD-001 | Batch records | Current approved master batch record and one completed representative batch | High | 2026-08-10 | Production record owner | In progress | MBR-014 Rev 6; BPR-24017 | QA batch review | Fictional example: verify all deviations and reconciliation links. | Open
AUD-002 | CAPA | Effectiveness evidence for recurring documentation CAPA | Critical | 2026-08-06 | CAPA owner | Blocked | CAPA-2026-031 | QA systems | Blocked pending defined observation window. | Open
AUD-003 | Data integrity | Audit-trail review procedure and sampled evidence | High | 2026-08-14 | System owner | Ready for review | SOP-DI-008 Rev 3 | Data governance reviewer | Sample preserves exceptions and review decisions. | Open
Formulas:
Attention = IF([Evidence request or control]="","",IF([Status]="Closed","Closed",IF([Due date]="","Needs due date",IF([Due date]<TODAY(),"Overdue","Open"))))

## Sources & Control
Sources, applicability, limitations and sign-off
Source ID | Title | Official locator
ICH-Q9-R1 | Quality Risk Management Q9(R1) | https://database.ich.org/sites/default/files/ICH_Q9-R1_Guideline_Step4_2022_1219.pdf
ICH-Q10 | Pharmaceutical Quality System Q10 | https://database.ich.org/sites/default/files/Q10_Guideline.pdf
FDA-DI-2018 | Data Integrity and Compliance With Drug CGMP | https://www.fda.gov/regulatory-information/search-fda-guidance-documents/data-integrity-and-compliance-drug-cgmp-questions-and-answers
Applicability and limitations
Use only within the confirmed product, process, jurisdiction, approved procedure and reviewer scope. Verify current editions, licensed compendial text and site-specific requirements. The workbook does not provide release, validation, engineering or regulatory approval.
Control field | Entry
Prepared by role
Reviewed by role
External approval reference
Review date

## Lists
Editable controlled lists
List | Allowed value | Purpose | Change note
D | Low | Allowed value for column D | Change only through workbook version review
D | Medium | Allowed value for column D | Change only through workbook version review
D | High | Allowed value for column D | Change only through workbook version review
D | Critical | Allowed value for column D | Change only through workbook version review
G | Not started | Allowed value for column G | Change only through workbook version review
G | In progress | Allowed value for column G | Change only through workbook version review
G | Blocked | Allowed value for column G | Change only through workbook version review
G | Ready for review | Allowed value for column G | Change only through workbook version review
G | Closed | Allowed value for column G | Change only through workbook version review